## Instructions
URLs
7/21 video | https://epa.connectsolutions.com/p737zn4ooqr/
7/24 video | https://epa.connectsolutions.com/p6zbmbobl7c/?launcher=false&fcsContent=true&pbMode=normal
Timecodes are approximate, so go back a few seconds if you think you are not getting everything.
"0" (zero) in the timecode is for a global edit or note. If there's a timecode, then I can see it onscreen.
Type = ? = I'm asking a question. Not necessarily prompted by anything onscreen.
Type=UG, I'm flagging a place I want to come back to for user guide material. Such as Tom explaining the column assignments from openLCA, reassigning columns, etc. You can filter out the UG rows.

## 7-21
Timecode | Type | Location | Issue | Assigned To | Difficulty (1-5) | Status
3:00 | Style | Splash screen | Add new logo, splash screen
3:00 | Style | Splash screen | Should splash screen have a copyright date?
7:06 | Style | Paths Preferences | Rename Choose Storage Location dialog
7:06 | Style | Paths Preferences | Revise dialog box text to a single sentence: "Specify a directory where the Harmonization Tool will store its working files."
8:00 | Feature | Paths Preferences | Remove the "Choose individual locations" option; make display of working directories non-optional.
8:00 | Style | Paths Preferences | Change button label to "Browse…"
8:00 | ? | Paths Preferences | Limitation of special characters or number of characters in pathname? Best practice to pick the shortest path possible or does that matter?
8:37 | Feature Discussion | Paths Preferences | Change dialog box layout so that common directory is at the top of the box, and only the differences are listed below. MEB suggests keeping full paths visible as is, per Msft's example in Msft Word and Excel Save Preferences dialog.
8:37 | Style | Paths Preferences | Change all misspelled "Direcotry" to "Directory" (4 changes)
8:37 | Style | Paths Preferences | Left-align the last two text boxes with the boxes above
8:37 | Style | Paths Preferences | Change "sets preferences" to "Customize Harmonization Tool working directories."
9:45 | Style | Paths Preferences | Change "Triples database Directory" to "RDF Directory"
10:00 | Feature | Paths Preferences | Can Eclipse add tooltips to the labels of the Preferences dialog? They could provide more info on each directory type.
10:40 | Feature | Preferences | The lefthand preferences panel is in white with a Filter text box at the top. Is there a way to remove the "type filter text" text box?
10:54 | Feature | User Preferences | Left-align the text fields so they're not ragged-left.
10:54 | Feature | User Preferences | Change text: "Complete the fields below to associate your information with dataset annotations made using the HT." SHOULD THIS BE A REQUIRED STEP?
10:54 | Feature | User Preferences | Change "User Preferences" to "User Metadata" or "Annotation IDs"?
10:54 | ? | Paths Preferences | If I click OK but not Apply, are my changes saved?
11:08 | Feature | Info box | Change status dialog text to "Initializing triple-store database…"
12:10 | ? | Paths Preferences | Clicking "Restore Defaults" button reverts to machine-assigned defaults, with is the user's home directory. ASK WES IF THIS IS WHAT HE WANTS.
13:52 | Style | Logger | Change Logger to Log File? Or just Log?
14:00 | Feature | UI | Consider adding a global status bar -- where would it go?
14:23 | ? | Contexts tab | We need to explain what the "(user data)" means. Is it possible to have dummy placeholder text here, like "No dataset loaded/"
0 | Feature | Global | Would be nice to remove the X and Window icons from all tabs. I think most users are OK with tabs and understand how they work. (I'm using "tab" because that's what they look like and that's how I'll refer to them in the user guide, unless there is strong objection to this.) For this release, dumbing down the UI may be useful in restricting the user to take the paths we want them to take.
15:20 | Feature | SPARQL panels | Remove them from the UI. Also remove the Output Harmonized Data tab.
16:15 | Style | Flowables | Add text for user at start of process to explain why the tab is blank? Explain its purpose?
16:25 | Style | Inventory Workflow | Add ellipsis to Load User Data button
17:48 | Style | Dataset Metadata | Suggest changing dialog box name to "Dataset Properties". If you're opening someone else's dataset, then you won't edit it except for Comments. Be default, you're viewing it.
17:48 | Style | Dataset Metadata | Remove the white space at top of dialog.
17:48 | Style | Dataset Metadata | Put dialog box name in the dialog's title bar (as with the Open dialog at 17:07 and the Preferences dialog.
17:48 | Style | Dataset Metadata | Change "Data Set Information" to "Dataset Properties". Change File Information to "File Properties". Change "Data set name" to "Dataset name".
17:48 | Style | Dataset Metadata | Put some space between the labels and the text boxes. They're way too close.
18:42 | Feature | Dataset Metadata | You can load multiple files and associate them with a single dataset. The master lists are already loaded and viewable from picklist but SHOULD NOT be associated with a dataset. POSSIBLE TO KEEP THEM OFF OF THE DATASET NAME PICKLIST? OR GREYED OUT? If you don't want the user to do anything with them, then remove them. OR MAKE MASTER LISTS NON-EDITABLE IN THE DIALOG?
19:55 | ? | Dataset Metadata | By selecting a master list, you can see metadata for that master list. Tweak the UI so the user can see this metadata?
20:22 | Feature | Dataset Metadata | No character limit in Comments box. Should a scroll box appear if you have a lot of text?
20:22 | Feature | Dataset Metadata | Carriage returns are allowed in Comments box but no other text boxes. Suggest removing this feature as pressing Enter usually connotes clicking OK button. And in you hit Enter in any other box, it loads the selected dataset. The user could use Shift+Enter to add new lines to the Comments box.
20:57 | Feature | Workflow | Should status boxes be grey rather than yellow to reflect they are not editable by the user?
21:23 | Style | Data Set menu | Change menu name to Dataset. Change Edit Metadata to Edit Properties. (I'm focused on Properties nomenclature since I'm working in Windows, but Metadata could work here too.) Change Load Data Set to Load New Dataset.
0 | ? |  | Can you have more than one dataset loaded in HT at a time? But you can only HARMONIZE one dataset at a time?
25:25 | UG | User Data tab | Column names from openLCA, reassigning column names, | MEB
26:58 | Bug | User Data tab | Remove "Ignore Column" tooltip; replace with "Change Assignment"
28:20 | UG |  | More on columns: 3 flowable columns, 2 flow context columns, 2 flow unit columns | MEB
29:40 | UG |  | Check Data button functions. | MEB
30:51 | Feature | Workflow | Enable user to edit data in the User Data window. Errors must be corrected before moving on to Commit. * You can ignore a row.
31:05 | UG | User Data tab | Left click on index ID to ignore a row. Allows you to move forward with erros in yr data. | MEB
31:40 | Feature | User Data tab | Make it possible for user to ignore a specific table value (treat it as blank or just don't parse it) rather than a whole row, but have to decide what are implications for the rest of the row.
32.07 | UG | Logger | Lists the errors found during the Check Data process - where issue is and what type of issue | MEB
32.50 | UG | Commit | Key concepts of harmonization: several tiers (automatic, if user wants to search db to find a match or a suggested match) | MEB
34.25 | Feature | Commit | Instead of percentages, what about a progress bar? As it creeps along, the user is getting feedback.
34:28 | Bug | Load User Data | Grey out this button after Commit is complete? When will the user decide they're finished?
35.17 | UG | Coloring | In windows, coloring is a bit wonky. Only some rows are colored, depending on match conditions | MEB
36.37 | Feature | Workflow | Musing on changing names of buttons 4-6 - probably superseded by 7/24 video
38.10 | UG | Workflow | Suggest user starts by matching all of the contexts | MEB
38.35 | UG | Workflow | If 8 out of 8 matched…, you could just confirm what you see. Use the Contexts tab. | MEB
39:24 | UG | Contexts tab | What the legend on the tab means, green+gray = assigned, if you unassign it all turns yellow along with the associated cells and no grey highlight in Contexts tab. To asign, simply click a context in the list, it turns grey and the cells turn green. The status box by the button updates along with this. | MEB
39:54 | Bug | Contexts tab | After clicking Unassign, should it then become disabled or its label switched to Assign?
40:55 | UG | Contexts tab | Click Next button to go to next row in User Data | MEB
0 | UG |  | Would be really useful to do a narrated Camtasia of this process, pointing out all the features. Would take less time to watch the video than to read about it. Maybe later. | MEB
41:39 | UG | Contexts tab | The yellow shows that "land, unspecified" was not enough to assign a context. | MEB
42:23 | Feature | Contexts tab | Disable the Next button when there are no more contexts to skip to? Or cycle back to the top?
42:37 | UG | Contexts tab | User should go through them because there won't be many. 4-15, typically. Can be done quickly by clicking Next and selecting resource. When done, they should see 8 of 8. | MEB
43:43 | UG | Properties tab | Click the button to show in User Data and switch to Properties tab. | MEB
44:00 | Bug | Properties tab | Assigned item in list is green instead of grey.
45:11 | Bug | Properties tab | The m3 property is not listed first under "volume", which it should be since it is the default. List looks alphabetized.
45:56 | UG | Properties tab | Language is tricky around flow property and flow unit. Be clear about what's happening so the user understands. | MEB
46:47 | UG | Flowables | will take more time bec more of them. Click Match Flowables to show those rows. Also highlights the row coloring bug (i.e., they should be colored but aren't) | MEB
47:30 | Bug | User Data tab | Tom clicking on rows to see them change color. Rows 26-27 are yellow when showing all rows, but white when filtered to Flowables.
48:20 | UG | User Data tab | Note the "13/27" in the index column header. Indicates 13 green rows of 27 visible. But what does this have to do with the matched contexts, etc. What does it mean when the cells are yellow but contexts and properties have been matched? | MEB
48:40 | Bug | User Data tab | Showing all rows, row 6 is partially white instead of all green.
48:49 | UG | Flowables | Focus on flowables tab. Green = match, yellow = no information, orange = some information but not a definitive match. | MEB
49:50 | Bug | Flowables | Unassigning a flowable in the tab turns the row orange, but the User Data row remains yellow. Should it be also orange?
50:25 | UG | Flowables | Click Next to go to next UNMATCHED rather then MATCHED, as in contexts and properties. Since there are so many flowables, more time efficient to only skip to the next UNMATCHED | MEB
50:36 | Feature | Flowables | Add a Next Unmatched button to go with Next button?
51:00 | UG | Flowables | When the user text does not exactly match the master list text, but it's still green to show assignment. Bec there is a match in the master list synonym. Case insensitive. | MEB
51:51 | UG | Flowables | Nitrous Oxide. No match. User needs to know: Click on the row (in User Data or in Flowables tab?) and the HT does a second check that is slower, looking for name or CAS matching. Logic: do what's fastest first to get a match, and do the slower match (1 sec) for problem matches. * Enter a search. LOGGER feeds back search transaction | MEB
54:20 | UG | Flowables | Doing a wildcard search. Only first hundred are returned. To see more, click the 100- button. (Should tht be 100+?). Logger will show how much more are found. | MEB
55:13 | UG | Flowables | When searching, the HT may return non-obvious matches. What is probably happening is that the search term is found in one of the term's synonyms in the master list. | MEB
55:20 | UG | Flowables | Watch what happens when assignment is made. * flowable and flow turned green. Now the HT knows the flow so it matches the flow and now have 14/27 rows matched. | MEB
56:48 | Bug | Flowables | When you do a search, then add an extra search term, the first row of returned results gets assigned.
57:10 | Feature | Flowables | Assigned water to the flowables but did not cause row 26 to be assigned a flow. Tom tries other water options but it does not match the flow. Make it so you get a hint from the HT ; search on "water*" and the most likely choice sorts to the top.
58.50 | UG | Flowables | Explicit difference only intended to be used when you have two things are really different but there is some other indication that they're the same. In principle, you can select more than one row from the search. But practically, for now, select only one. | MEB
1:00:00 | UG | Flowables | You cannot copy or paste from search returns into the search box. You can search on text or a CAS number | MEB
1:01:00 | UG | Edit Metadata dialog | X is for deleting dataset. (From disk? Or just the picklist?) | MEB
1:01:00 | Feature | Edit Metadata dialog | Change tooltip for X button from "data set" to "dataset". Also, specify whether you're deleting the dataset "from disk" or "from LCA-HT".
1:01:23 | Style | Confirm dataset delete | Change "Confirm Deletion" label to "Confirm". Buttons should be in the standard OK/Cancel order, so Confirm/Cancel. Specify whether removing the dataset from disk or just unloading from HT Am also assuming any work you've done on the dataset during the current session will be lost. Change 'data set' to 'dataset'
1:01:33 | Style | Rename dataset | Title bar should say "Rename Dataset" Remove the "Please type…" sentence as it should be obvious from the title bar. OK/Cancel should be in the lower right of the dialog The dialog should probably be smaller; doesn't need to be this big, anyway
1:01:45 | Feature | Edit Metadata dialog | Tom muses: ensure the Rename and Delete work or just remove them? I'd say remove them and put enhancements into v2.0, unless you consider dataset mgmt to be core functionality. I think flow matching and harmonization functions are more important. Let the users know in the UG how to rename or delete OUTSIDE of lcaht?
1:02:15 | UG |  | what do we mean by dataset? You could have a single dataset made up of 5 files. | MEB
1:02:45 | Feature | Edit Metadata dialog | There should be a separate "Delete Dataset…" menu item
1:02:55 | Style | Dataset menu | Rename Load Data Set to Reload Dataset?
1:03:20 | Style | Load Dataset dialog | Title bar should say "Reload Dataset" Change sentence to "Select a dataset to reload:" (now says EXPORT)
1:03:55 | Feature | Tab X's | Tony was working on making the X's nonfunctional
1:05:30 | Style | SPARQL menu | Rename to Advanced
1:05:30 | Feature | SPARQL menu | Add canned queries
1:06:05 | Style | About dialog | Title bar should say "About LCA-Harmonization Tool" Drop the sentences. Just say: HT version 1.0.xxxxxxxx Database version 1.xxxxx For support, contact <email@address>
1:07:05 | Style | File menu | Possible to put separators in menu dividing categories of menu items? Something like Load ¦ Save commands ¦ Export ¦ Preferences ¦ Exit
1:07:05 | Feature |  | Add a Tools or Options menu with the single command Preferences. This is fairly standard in the Windows world. (Maybe rename SPARQL to Tools, list Export Database, then the queries, then have Preferences or Options for the Preferences dialog at bottom of the menu.)
1:09:05 | UG | Load Reference Data | Use a diff master list or a supplementary list. With a large dataset, and you know if has lots of CAS numbers, it could help you search against the master list. | MEB
1:10:05 | UG | Save CSV | Displays a table where you can specify stuff. Check prev version. | MEB
1:10:55 | UG | Save Harmonized (json) |  | MEB
1:10:55 | Style | Save Harmonized (json) | Dialog box titlebar should echo the File menu command name "Save Harmonized Data (json, ttl, zip) Change data set to dataset
1:11:36 | UG | Save Harmonized (json) | Document the choices and what they are: json, jsonld (same as json), turtle (mainly for development use), zip (prepping for openLCA - runs a separate algorithm). The zipped json choice | MEB
1:12:30 | Feature | Save Harmonized (zipped json) | Move this functionality from File menu to the Export Harmonized Data button
1:12:48 | Bug | Save Harmonized (zipped json) | HT presents you with the export dialog twice. Should only be once.
1:12:30 | Feature | Save Harmonized (zipped json) | Show percent complete in status as files are being zipped (or progress bar?)

## 7-24
Timecode | Type | Location | Issue | Assigned to | Difficulty (1-5) | Status
8:00 |  |  | Discussion with Wes; spreadsheet showing flows that are not matched up between the current master list and the openlca flows | Tom
12:50 | Feature | Splash screen | Maybe add a progress bar as it loads | Tony
12:50 | Feature | Splash screen | Add Wes's logo | Tony, Tom
13:35 | Feature | Choose Storage Location | Display a message if running LCA-HT the first time? Ie, "Choose your workspace." Where will the TDb live? And your workspace? Where would you like to store your projects? What is the project name? Do you want to work on an existing project or create a new one? "Choose a database storage location." "Choose a project and project directories." - Choose a database location. Then, where do you want to store yr project and what is your project called? Then, when you log in again, you can select from an existing list of projects. | Tom
14:30 | Feature | Choose Storage Location | see row 5 in the other sheet | Tom
| Feature | Choose Storage Location | LCA-HT could see if choices exist from previous runs and offer those via a picklist | Tom
| Feature | ? | Instead of "dataset" as a place that can hold >1 files, what about "Project" - so you'd edit a project's metadata, a project could contains multiple datasets, etc. | Tom
| Feature | Choose Storage Location | If you want to use a new TDB, specify it here. | Tom
| UG | Paths Preferences | The tdb path tells you where the projects are | MEB
17:57 | Feature | Choose Storage Location | Add checkbox that says, "Do not show this again." it could be checked by default. Or they could uncheck it in the preferences. (Wes) | Tom
| Bug | Rename dataset | Verify if this functionality works. | Tony, Tom
20:00 | Feature | SPARQL Results tab | Leave it closed. Need Wes to decide on what goes in the query results tab. Tab would only display if that query is selected from menu. Change tab name to "Query Results" ; hiddne until user asks for it. | Tom, Wes
20:40 | Feature | File Menu | Add "Show Dataset Contents" query to File Menu | Tom
22:57 | UG | Loading data | Document what data should be in the CSV and zipped json files. Tom will have to tell me this. Be specific about what should be in the csv | MEB
23:40 | Bug | Rename dataset | Revise to "Change Dataset Name" DOES IT WORK?? | Tony, Tom
24:10 | Feature | Edit Metadata dialog | Add a User Dataset option? For now, leave alone. See comments on 7-21 sheet In future, user could create their own masterlist | -
0 | Feature | Edit Metadata dialog | Could we present the Master List/Supplementary Dataset options so they're more clear as to their purpose or what feedback they present to the user? Such as, click Master List to view only master lists. Because you can't change metadata for a master list and you can't make something a master list by clicking this option. | MEB, Tom
25:40 | Feature | Status of loading | Make the status a single percent number | Tony, Tom
26:50 | UG | Cancel Harmonization button | Document what this is supposed to do. And then what HT and the user are to do next: load a new dataset? Start over? | MEB, Tom
28:00 |  | Workflow | Discussing the Commit button, labels, harmonization, data not yet saved to TDB till Commit is pressed | -
| Feature | Workflow | Instead of Commit: Save Unharmonized Data and Start Autoharmonization - SUPERSEDED - SEE LATER COMMENTS | -
29:30 | Feature | User Data | Wes - For the column headers, category and subcategory are more familiar to the user community. Go back to those. | Tom
34:30 | Feature | User Data | Discussion of context/subcontext, category/supercategory. Wes asked for a third level. All flow context info is in one column titled Flow Context, concatenated by semicolons. Will take anything in user data and follow to highest level of parent up to elementary flows (which is an openlca convention). 36:00. Tom - when you import CSV data, then you can assign as many columns as you want to the flow contxt. And HT will concatenate with semicolons and then parse that. Assuming left to right ordering. 36:17. Wes: Call the column Flow Context 1, 2,3 Tom: how should csv column headers be assigned? In output, if not in the right order, would concatenate oddly. We'll pick the easiest thing that could work. | Tom
34:30 | UG | Flow Contexts | All flow context info is in one column, concatenated by semicolons. Will take anything in user data and follow to highest level of parent up to elementary flows. Tom - when you import CSV data, then you can assign as many columns as you want to the flow contxt. And HT will concatenate with semicolons and then parse that. Assuming left to right ordering. | Tom
38:45 | Feature | Flow Unit:Property | Discussion. Naming is ok for now. | -
39:25 | Bug | UUID | Tom: annoyig that the font is not justified. | -
40:27 | Feature | Logger | Tells you which columns have issues but is too verbose. Make it simpler? More important to do something about the issues. | Tom
40:57 |  | User Data | Wes is OK with CAS and Formula columns being blank | -
41:44 | Feature | Workflow | Wes-Status boxes should feed back percentages; a single number, rather than 1/4, 2/4, etc. | Tom
42:07 | Feature | Workflow | Tom musing: Should status say units that are getting matched? No answer fronm wes | Tom
42:23 | Feature | User Data | The index column that shows "13/27": add mouseover "13 of 27 flows matched." | Tony, Tom
43:54 | Feature | Logger | Add above message "x of y flows matched" to Logger. | Tony, Tom
44:10 | Feature | User Data | Tom: add a second pass to ensure all flowables get colored. | Tom
44:36 | Bug | Flowables | Fix coloring on flowables: water should be green. water,fresh should be yellow. Water, salt ocean should be green. | Tom
46:00 | UG | Workflow | Prescribe that users match contexts and properties first. Provide justification for that (Wes). TT: if you're trying to pick a flowable, you could be guided by the flowable in context and the property in other flows. You want to find the most common and accurate match. | MEB, Tom
48:12 | Bug | Workflow | Click on land unspecified in User Data table, it highlights the row. But clicking on the cell and dragging does not pick up the click. The scrolling inhibits the row click. Same for energy -- if you need to resize the column, the bug is triggered. The scrolling screws up the row-clicking | Tom
50:05 | Bug | Master Lists | In Contexts, assigned item should be green (as it is in Properties). Assigned context should be in green. | Tony, Tom
52:05 | Bug | Properties/Volume | Cubic meters should be at the top. Reference units should be at the top. | Tom
52:35 | Feature | Properties | How are reference items in masterlists flagged? Boldface and mouseover are simple. For the reference item, mousesover would say "Reference (Conversion factor = 1)." For all other items, mouseover gives conversion factor. | Tom
52:35 | UG | Properties, Contexts | How are reference items in masterlists flagged? Boldface and mouseover are simple. For the reference item, mousesover would say "Reference (Conversion factor = 1)" For all other items, mouseover gives conversion factor. | MEB, Tom
53:40 | Feature | Properties tab | Adjust unit values for exchanges and impact factors. High priority | Tom
54:45 | Check | CSV issue | Wes: if user has amount data with csv data, does that still get shown? Column to assign for amount? Tom - i think so. CHECK THIS. Wes will take typical csv data, run it through, and make note of bugs Reviewed process of creating csv output | Tom, Wes
58:50 | Feature | User Data | Get rid of Other column in Match Flowables. | Tom
58:00 | UG | Workflows | Confirm contexts and properties even if they're green. Match flowables is a slightly diff process from Contexts and Properties. | MEB, Tom
59:20 | Feature | Contexts, Priorities | Buttons: Next and Next Unmatched | Tom
1:00:30 | Feature | Properties tab | Rename to Units | Tom
1:01:10 | Feature |  | Change button to Match Units (?) SEE BELOW | Tom
1:01:15 | Feature | Workflow tab | Replace buttons with mix of static text labels and dynamic buttons. CHECK THESE AGAIN WITH WES BEFORE IMPLEMENTATION Status column is unchanged. Labels and BUTTONS would be: 1 User Data - LOAD or IMPORT 2 Format - CHECK, status=Checked 3 Save Match - GO 4 Context - toggle UNIQUE/ALL (ALL ROWS?) 5 Unit - toggle UNIQUE/ALL ROWS 6 Flowable - toggle UNIQUE/ALL ROWS 7 Finish - CANCEL or EXPORT - status would show % complete | Tom
1:06:00 | UG |  | Open second instance of HT only if a different tdb; otherwise, locked | Tony, Tom
1:07:30 | Feature | Flowables | Remove the picklist for Name/CAS. Ht should already be able to detect a cas; everything else is a name | Tom
1:08:00 | Feature | Flowables | Remove the Search button or move it to the far right of the text box. User should type text, press Enter, and the search starts. Be able to type in text, press Tab to Search button and hit Enter? Or just type text and hit enter? | Tony, Tom
1:09:35 | Feature | Flowables | Search box: text should right-align so it moves as you continue typing | Tom | 1
1:10:20 | Feature | Flowables | Move the "3 rows" box to left of NEXT button. When there is only one green row and one master list row, it is not clear currently what the "3 rows" refers to. | Tom
1:10:20 | UG | Flowables | When there is only one green row and one master list row, it is not clear what the "3 rows" refers to. It refers to the number of matched records in the User Data panel. | Tom
1:10:20 | Feature | Flowables | Move the "3 rows" box to left of NEXT button. Expand to say "3 rows contain" or "3 matched rows"? | Tom
1:12:20 | Feature | Flowables | Add NEXT UNMATCHED button to echo similar NEXT/NEXT UNMATCHED in Contexts and Properties | Tom
1:12:47 | Feature | Flowables | Fix "1 rows" so it says "1 row" when there is only 1 row. | Tony, Tom
1:14:20 | Bug | Flowables | Fix bug in match flowables regarding assign routine. Tom suspects this is caused by duplicate Comparison objects | Tom
1:16:00 | Feature | Export | Discussion. Some confusion about having the export formats in both File menu and as button pulldowns. | Tony, Tom
1:17:25 | Bug | Exporting | Description: when you choose the dataset and the file, you have to choose the dataset again. | Tony
1:18:05 | Feature | Export Dialog | Dialog should ask you to both choose the dataset and output format | Tony
1:18:00 | Style | Global | Data set should be Dataset Tom's discussion of when to use the term "data set"; use one word except when talking about a generic set of data | MEB, Tom
1:20:45 | Style | Global | TDB should be Database Database is a more normal term to hear Put it in UI | MEB, Tom