## Comments
Issue ID | LCA-HT Version | Date | By | Tab/Menu Item | Type | Comment | Response | Resolved? | Resolution explanation
1 | 20140224 | 2014-03-04 | WI | General | Feature Request | The matching processes should go through a more phased-approach as suggested in the LCA-HT_FlowMatching_Mock-Up, where categories then flow properties and units are matched and then flowables, rather than parsing categories and flowables separately. | Would like a better understanding of whether flowables and categories should be treated separately or not.
2 | 20140224 | 2014-03-04 | WI | Query - Show Dataset Contents | Question | Show DataSet Contents – Master_Flowables appears twice – once with Type ‘Flowable’ and once with ‘NamedIndividual’. Count is 979 for each. What is the type intended to represent? Is it important to show these as separate datasets? | OK, I understand that the query used is too broad. I'll work on a query that produces a more useful presentation of contents. This will be implemented as a button or menu option (see issue #9)
3 | 20140224 | 2014-03-04 | WI | Query | Feature Request | There is a delay between when queries are executed and when they show up in another query (such as Show DataSet Contents) , presumably because the previous query has not finished executing. We need a pop-up window or other notice to inform the user that a query is still running | At a minimum a list of jobs running with start time is necessary. Ideally, some functionality would be locked while some jobs are running.
4 | 20140224 | 2014-03-04 | WI | File Menu Commands - Import CSV | Bug | Should ignore first row or ask the user whether or not the first row should be ignored | Understood. | 2014-04-01 | User may select arbitrary rows and "ignore" or "use". Default is "use" for all.
5 | 20140224 | 2014-03-04 | WI | Save Results | Incomplete | Appears not to work | Fixed in latest version. | 2014-03-01
6 | 20140224 | 2014-03-04 | WI | Load TDB | Feature Request | Perhaps only the TDB folder could be specified here and the other options could be in the preferences menu instead. | Need a clarification. It is true that we've essentially obviated the need for the TDB menu. We've left it "just in case" and for testing.
7 | 20140224 | 2014-03-04 | WI | Data File Tab | Incomplete | Edit metadata does not work | This is mostly fixed. It turned out to work on the Mac, but now works in Windows. There is one bug left to fix. | 2014-03-01 | Nearly all aspects resolved. Remaining, is storage of list of files in TDB. These are currently only stored in memory while the HT is running.
8 | 20140224 | 2014-03-04 | WI | Query | Feature Request | Migrate these individual queries to another interface (perhaps a combination of dropdowns or series of popup menus) | I anticipate removing all of these in favor of building the necessary "buttons" into other features.
9 | 20140224 | 2014-03-04 | WI | Query | Feature Request | Instead of just displaying matches for the harmonization queries, show both the matched and unmatched flowables to the user can harmonize all of them | Yes, indeed unmatched flowables must be displayed. The difficult is in how to handle the process of annotating them, or proposing new additions to the master list. Will propose specific steps and begin implementation.
10 | 20140224 | 2014-03-04 | WI | Results tab | Feature Request | Need to be able to export results to .csv | Same as issue 5. Fixed. | 2014-03-01 | See #5
11 | 20140224 | 2014-03-04 | WI | Committing | Feature Request | User needs to be notified that matches are committed | Understood. A better "status" reporting mechanism needs to be implemented.
12 | 20140224 | 2014-03-04 | WI | Results tab | Feature Request | When harmonizing flows, categories and flow properties permit (1) equivalent, (2) proxy, (3) superset, (4) subset. A separate column may be needed to record the match type, defaulting to equivalent | In addition, we suggest (5) different. This would be used in cases in which evidence suggest they are the same.
13 | 20140224 | 2014-03-04 | WI | Results tab | Feature Request | Add another field to capture annotations for matches | Understood.
14 | 20140224 | 2014-03-04 | WI | Results tab | Feature Request | Need a temporary save option (not committing) and reload matches function to prevent users from losing work, or do an auto-save on a regular time interval | We can look into a "save state" function This may be preferable to using the TDB to save everything.
15 | 20140224 | 2014-03-04 | WI | Committing | Feature Request | Need an undo button to undo committed matches | Understood.
16 | 20140403 | 2014-04-03 | TRT | Data View | Data completeness | When importing data, some fields must be defined. There may be only one value for the entire data set, or a value may be inferrable from the value in another field. | A list of "types of data sets" should be established along with with what fields are necessary in each. Also, fields which can be inferred from others should be defined.
17 | 20140403 | 2014-04-09 | TRT |  | Feature Request | Export one data set with names from another - type query.
18 | 20140403 | 2014-04-09 | TRT | CSV file reading | Feature Request | Add the ability to "page" data for large files
19 | 20140403 | 2014-04-14 | TRT | Console | Bug | Results in error. It appears that messages go to console. This error does not occur when the console is closed.
20
21
Note on F1: Feature Request Bug Incomplete Question